## Slide 1
INTOSAI WORKING GROUP ON KEY NATIONAL INDICATORS
Dmitry Zaytsev
Accounts Chamber of the Russian Federation
Brasilia, Brazil, April 26, 2017
IX MEETING
WORKING GROUP PLAN FOR 2017

## Slide 2
WORKING GROUP PLAN FOR 2016
№ | Activities | Time | Coordinator
1. | The 10th meeting of the Working Group | April 25-27, 2017 Brasilia, (Brazil)) | SAI of Brazil, Secretariat, WG members
2. | Professional standard on auditing the use and development of key national indicators |  | 
2.1 | Developing the subproject “Key national indicators systems and public governance | March, 2018 | SAI of Brazil, WG members
2.2. | Agreeing the Initial assessment and the Project proposal with the WG members | April, 2017 | Secretariat, WG members

## Slide 3
WORKING GROUP PLAN FOR 2016
№ | Activities | Time | Coordinator
2.3 | Agreeing the Initial assessment and the Project proposal with the KSC Steering Committee and the FIPP | November, 2017 | Secretariat
2.4 | Developing the draft ISSAI on auditing the use and development of key national indicators | Entire period | Secretariat, WG members
3. | The 9th KSC Steering Committee Meeting, August 23-25, 2017, Bali, Indonesia |  | 
3.1. | Preparing the report on the Working Group activities 2016-2017 and agreeing it with the WG members | August 1, 2017 | Secretariat, WG members

## Slide 4
WORKING GROUP PLAN FOR 2016
№ | Activities | Time | Coordinator
3.2 | Presentation of the report on the Working Group activities 2015-2016 at the 9th KSC Steering Committee Meeting | August 23-25, 2017 | Secretariat
4. | The 70th INTOSAI Governing Board Meeting, November 6- 7, 2017, Graz, Austria |  | 
4.1 | Preparing the report on the Working Group activities 2016-2017 and agreeing it with the WG members | October 1, 2017 | Secretariat, WG members
4.2. | Presentation of the report on the Working Group activities for 2016-2017 at the 70th INTOSAI Governing Board Meeting | November 6-7, 2017 | Secretariat

## Slide 5
WORKING GROUP PLAN FOR 2016
№ | Activities | Time |  | Coordinator | 
5. | Knowledge Base on KNI |  |  |  | 
5.1 | Developing the website of the Knowledge Base on KNI |  | Entire period |  | Secretariat
5.2 | WG member-states designated persons providing the Secretariat with the information about national SAI to be placed on the Knowledge Base website |  | Entire period |  | WG members
5.3 | Monitoring of the international initiatives in the sphere of the assessment of the socio-economic development taking into account recent developments in this sphere |  | Entire period |  | Secretariat, WG members

## Slide 6
WORKING GROUP PLAN FOR 2016
№ | Activities | Time | Coordinator
6. | New framework agreement between INTOSAI and OECD | Entire period | Secretariat
7. | Developing the Initial assessment and Project proposal on auditing the macroeconomic forecasts | Entire period | Secretariat
8. | Developing contacts with the UN, the WB and other organizations on the SDG 2030 issues | Entire period | Secretariat, WG members
9. | Developing cooperation with the INTOSAI Working Groups and regional economic organizations | Entire period | Secretariat, WG members
10. | Preparing the 11th meeting of the Working Group on KNI | Entire period | SAI of Italy, Secretariat, WG members

## Slide 7
IX MEETING
THANK YOU!
INTOSAI WORKING GROUP ON KEY NATIONAL INDICATORS