Draft

INTOSAI Working Group on Key National Indicators

Working Plan for 2017

|  | Activities | Time | Coordinator |
| --- | --- | --- | --- |
|  | The 10th meeting of the Working Group | April 25-27, 2017 Brasilia, (Brazil) | SAI of Brazil, Secretariat, WG members |
|  | Professional standard on auditing the use and development of key national indicators |  |  |
| 2.1. | Developing the subproject “Key national indicators systems and public governance | March, 2018 | SAI of Brazil, WG members |
| 2.2 | Agreeing the Initial assessment and the Project proposal with the WG members | April, 2017 | Secretariat, WG members |
| 2.3 | Agreeing the Initial assessment and the Project proposal with the KSC Steering Committee and the FIPP | August, 2017 | Secretariat |
| 2.4 | Developing the draft ISSAI on auditing the use and development of key national indicators | Entire period | Secretariat, WG members |
|  | The 9th KSC Steering Committee Meeting, August 23-25, 2017, Bali, Indonesia |  |  |
| 3.1. | Preparing the report on the Working Group activities 2016-2017 and agreeing it with the WG members | August 1, 2017 | Secretariat, WG members |
| 3.2. | Presentation of the report on the Working Group activities 2015-2016 at the 9th KSC Steering Committee Meeting | August 23-25, 2017 | Secretariat |
|  | The 70th INTOSAI Governing Board Meeting, November 6- 7, 2017, Graz, Austria |  |  |
| 4.1. | Preparing the report on the Working Group activities 2016-2017 and agreeing it with the WG members | October 1, 2017 | Secretariat, WG members |
| 4.2 | Presentation of the report on the Working Group activities for 2016-2017 at the 70th INTOSAI Governing Board Meeting | November 6-7, 2017 | Secretariat |
|  | Knowledge Base on KNI |  |  |
| 5.1 | Developing the website of the Knowledge Base on KNI | Entire period | Secretariat |
| 5.2 | WG member-states designated persons providing the Secretariat with the information about national SAI to be placed on the Knowledge Base website | Entire period | WG members |
| 5.3 | Monitoring of the international initiatives in the sphere of the assessment of the socio-economic development taking into account recent developments in this sphere | Entire period | Secretariat, WG members |
|  | New framework agreement between INTOSAI and OECD | Entire period | Secretariat |
|  | Developing the Initial assessment and the Project Proposal on auditing the macroeconomic forecasts | Entire period | Secretariat |
|  | Developing contacts with the UN, the WB and other organizations on the SDG 2030 issues | Entire period | Secretariat, WG members |
|  | Developing cooperation with the INTOSAI Working Groups and regional economic organizations | Entire period | Secretariat, WG members |
|  | Preparing the 11th meeting of the Working Group on KNI | Entire period | SAI of Italy, Secretariat, WG members |