The INTOSAI Working Group on Key National Indicators

Working Plan for 2011

|  | Activities | Time | Coordinator |
| --- | --- | --- | --- |
|  | The 4th meeting of the Working Group | April 13-14, Helsinki (Finland) | SAI of Finland, WG Secretariat |
|  | Determination of coordinators and preparation of the subprojects realization plan | April-June | WG members |
|  | 2.1 Preparation of Draft Methodology on the KNI selection for the use in SAIs activity | 2011 |  |
|  | 2.2 Analysis of opportunities on the use of KNI for international comparisons and preparation of appropriate recommendations | 2012 |  |
|  | 2.3 Investigation of opportunities of KNI use for the evaluation of the results of national and transnational projects and programs audit | 2012 |  |
|  | 2.4 Methodic and informational support of the KNI selection for the assessment of global economic imbalances | 2013 |  |
|  | Monitoring and analysis of the best practices of international comparisons in the sphere of the socio-economic development taking into account recent investigations in this sphere including researches of N. Sarkozy Commission on the Measurement of Economic Performance and Social Progress | September | WG Secretariat, WG members |
|  | Draft Methodology of the KNI selection for the use in SAIs activity | December | WG Secretariat, WG members |
|  | Preparation of the Chairman report on the Working Group activity at the 61 INTOSAI Governing Board | October 15 | WG Secretariat, WG members |
|  | Chairman report on the Working Group activity at the 61 INTOSAI Governing Board | November | The Chairman of the WG |
|  | Preparation of the White Paper on KNI as Draft Guide on the development and use of KNI in SAI activities for INTOSAI members’ consideration | November-December | WG Secretariat, WG members |
|  | Methodic and informational support of the visualization and assessment of KNI for the use in SAIs activity for the purpose of international comparisons | 2011-2012 | SAI of the Russian Federation, WG Secretariat |
|  | Knowledge Base on KNI information content | The whole period | WG Secretariat, WG members |
|  | Cooperation with the OECD within the framework of the Memorandum of Understanding | The whole period | WG Secretariat, WG members |
|  | Contacts development with the WB, the WEF and other organizations | The whole period | WG Secretariat, WG members |
|  | Cooperation development with INTOSAI Working Groups and regional economic organizations | The whole period | WG Secretariat, WG members |
|  | Maintenance of the INTOSAI Working Group on KNI website | The whole period | WG Secretariat, WG members |