## Slide 1: Documentation Requirements of an IT Audit including Audit Management System (Area: Audit Process)
A presentation by
SAIs AFROSAI-E, Bangladesh, China, Ecuador, Georgia, India, Indonesia, Iraq, Kuwait, and Mexico

## Slide 2: AGENDA
Project Synopsis (Project 5)
Project Plan 1 (Documentation Requirements of an IT Audit)
  Original project plan
  Updated Project plan
  Deliverables
  Project Plan Changes
Project Plan 2 (Audit Management System)
  Original project plan
  Updated Project plan
  Deliverables
  Project Plan Changes

## Slide 3: 1. Project Synopsis
Documentation Requirements of an IT Audit including Audit Management System (Area: Audit Process)
Introduction
At 24thWGITA meeting, it was discussed that WGITA in collaboration with IDI may consider developing AMS and it was decided to conduct a survey during 2015, 16 of 23 respondents were in favour of inclusion of AMS as a project, however, as many members have also shown interest for the project on: “Documentation Requirement for an IT audit”, Audit Management System may be included as part of this project 5, to achieve the resulted scope, two subprojects were defined:

## Slide 4: Project Synopsis
Subproject 1, Documentation requirements of an IT Audit
Taking in consideration the overall documentation requirements in an IT Audit would essentially flow from Level 3 ISSAIs viz~ ISSAIs 100, 200, 300 and 400, the approach of this subproject is to conduct a survey to identify specific adjustment to the documentation process in an IT Audit.
Subproject 2 Audit Management System (AMS)
For the development of a useful AMS for the different SAIS, it was proposed to initiate the project with the identification of a Generic Audit Process or part of the process that is common and produce value to the majority of SAIs, define this process in tree steps:
The first approach of a Generic Audit Process with functional requirements will be developed by members of project 5.
The Generic Audit Process will be enhanced with the feedback of members of the WGITA.
With the enhanced version, a survey will be conducted with all SAIs
With the result of the survey, a feasibility analysis for the AMS will be done, and if the AMS is feasible, a business case will be developed.

## Slide 5: 2. Project Initiation Document
1. Documentation requirements of an IT Audit
Issues to be covered/Scope of the project
The survey will identify specific adjustments to the documentation process of an IT Audit in each of the following phases:
Planning
Execution
Reporting and Follow up
Termination
Archiving and disposal
The level of standardization of the documentation in terms of checklists, specimen letters, organization of working papers, and the retention and protection requirements of the documentation.
Deliverables
Guideline with the description of the specific adjustments in the documentation process of an IT audit in each of the following phases:
Planning
Execution
Reporting and Follow up
Termination
Archiving and disposal

## Slide 6: Original Project Plan 1 Documentation requirements of an IT Audit

## Slide 7: Updated Project Plan 1 Documentation requirements of an IT Audit

## Slide 8: Documentation requirements of an IT Audit Deliverables
Survey applied to Project 5 members
Example of Mexican SAI survey
Survey adjustment (feedbacks from Project 5 members)

## Slide 9: Project Plan Changes (Documentation Requirements of an IT AUdit)
Decision to conduct a survey
Elimination of a second survey
The new project plan will take 3 more months than the original

## Slide 10: 3. Project Initiation Document
Audit Management System (AMS)
Issues to be covered/Scope of the project
In order to identify if there is a Generic Audit Process or part of the process that is common and produce value to the majority of SAIs:
A first approach of a Generic Audit Process with functional requirements will be developed by members of this project.
An enhanced version of the Generic Audit Process with functional requirements will be developed with the feedback of the members of the WGITA.
A survey will be conducted with all SAIs to identify if the result is Generic Audit Process or part of the process is common to the majority of SAIs and the level value that the functional requirements produce to each SAI.
With the result of the survey, a feasibility analysis for the AMS will be done with the process or part of the process that produce more value to the majority of SAIs.
It the AMS is feasible, a business case will be developed describing: objective, scope costs, resources, sponsors, schedules, risks, tasks and benefits, and also a project plan with development phases, resources allocation, INTOSAI and external participation, milestones, project leader.
Deliverables
Generic Audit Management Process
Feasibility analysis
Business Cases (if it is feasible)
Project plan (if the business case is approved)

## Slide 11: Original Project Plan 2 Audit Management System

## Slide 12: Updated Project Plan 2 Audit Management System

## Slide 13: Audit Management System Deliverables
Investigation of Generic Audit Process, with available public SAI web information, and results of technical surveys, main conclusions
  Many SAIs follow the INTOSAI General Process
  SAIs own subprocess and activities, difficult to standardize at these levels
  Particular SAI attributions (related to the country regulation)
  Common use of commercial software for word processing, project management, spreadsheets (e.g. Ms Office, acrobat)
  Customization of risk assessment and control evaluation methodologies
  Common implementations of BI and data analytics applications (e.g. click view, Tableau)
With the analysis of the conclusions, the Generic Audit Process should take in consideration:
  Define general functionalities that could be customized to particular sub process and activities of each SAI
  Integrate standards and methodologies (v.g. risk management and control evaluation)
  Integrate commercial software for word processing, project management, spreadsheets (e.g. Ms Office, acrobat)
  Integration with BI and data analytics applications
  Generic Audit Process (First approach)

## Slide 14: Project Plan Changes (AMS)
Decision to conduct a global study
Elimination of a second survey and refinement deliverables
The new project plan be developed in the original schedule

## Slide 15
Thank You