## Slide 1: Progress Report on proposed GUID on Information System Security Audit
A presentation by SAI India for 27th INTOSAI WGITA

## Slide 2: Introduction - background
Project on drafting GUID on Information System Security Audit - part of SDP “2.8 - Consolidating and aligning guidance on IT Audit”
Revise ISSAI 5310 as “Guidelines on Information Systems’ Security Audit”
Include new section on Cyber Security
Recommended numbering for GUID 5100 - 5109 series (reserved for guidance on IT-audit)

## Slide 3: Introduction - background
Approved Project Duration: 22.06.2017 to 30.06.2019 (24 months) in line with approval of GUID by 2019 INCOSAI
Members of Project Team
  Lead: SAI India
  Members: China, Ecuador, Iraq, Kiribati, Poland, USA, ISACA

## Slide 4: Project Objectives
Align guidance with ISSAI 100 and revised GUID on IT Audit
Identify universe of information systems assets in use by audited entity
Identify potential threats and counter measures for mitigation and avoidance of risk exposure to assets
Evaluate internal controls already adopted by audited entity
Analyse Risk, quantified in terms of risk exposure
Issue recommendations, based on computed risk exposure
To be bridge between WGITA IDI IT Audit handbook and Standards

## Slide 5: Proposed Timelines and Progress Achieved
Due process milestones |  |  |  | 
Stage | Start Date | End Date | Expected Time in Total | Comments
Project proposal | 10.10.2017 | 30.11.2017 | 50 Days | Proposal and Detailed Outline approved
Exposure draft | 01.03.2018 | 31.07.2018 | 5 months | In progress
Exposure period | 01.11.2018 | 31.01.2019 | 90 Days | Yet to commence
Endorsement version | 01.02.2019 | 30.04.2019 | 3 months | Yet to commence
Final pronouncement |  | 30.06.2019 |  | Yet to commence

## Slide 6: FIPP requirements on Project Proposal
Initial Conditional Approval of Project Proposal, subject to providing preliminary structure of GUID
Detailed outline considered and approved by FIPP in March 2018 meeting
FIPP requirements:
  Not be voluminous
  Not be too technical and focus more on audit issues of IT Security
  Stand test of time and not require frequent update
STATUS: Directions to be adhered at drafting stage(s)

## Slide 7: Current Status
Following FIPP’s approval of outline:
  Finalising Exposure Draft of the GUID is in progress
  Detailed comments on proposed sections of GUID have been requested from all Team Members by April 30, 2018

## Slide 8: Proposal before WGITA
WGITA members are requested to take note of
  Progress Report
  Project Schedule
  Detailed Outline (circulated)
  Suggested that the guidance be named as
    Guidance on Auditing Security of Information Systems

## Slide 9: Thanks…