## Slide 1: Reporting Dashboard of WGITA
Notes: NOTE:
To change the image on this slide, select the picture and delete it. Then click the Pictures icon in the placeholder to insert your own image.

## Slide 2: Reporting Dash board
INTOSAI Goal chairs to present Reporting dashboards, consolidating reporting dashboard of Working Groups
WGITA required to prepare half-yearly reporting dashboard
Dashboard to:
  Be aligned to KSC Strategies
  Be brief
  Bring out priorities, progress, challenges and key next steps
Second reporting Dash board of WGITA

## Slide 3: Objective - 1
Develop and maintain expertise in various fields of public-sector auditing and help to provide content to INTOSAI Framework for Professional Pronouncements

## Slide 4: Development/Revision of INTOSAI products
Progress indicator | Action items and other comments
3 non-IFPP documents on Data analytics, Capacity Development support for IT Audits and Documentation requirements of an IT Audit to be developed by 2019 Roadmap for Development of Roadmap for future GUIDs under 5300 Series (now 5100) to be completed by 2019 | Progress to date PIDs of project approved in 26th WGITA meeting Deliverables expected by 2019 QA level of documents identified: Data analytics,(QA-2), Capacity Development support for IT Audits (QA-3), Documentation requirements of an IT Audit(QA -2) Action items/Key next items Project teams carrying out research and consultations to prepare draft documents QA Process being followed up

## Slide 5: Development/Revision of INTOSAI products
Progress indicator | Action items and other comments
Revision of ISSAI 5300 & 5310 being taken up as part of SDP, is to be placed at INCOSAI 2019 for approval | Progress to date Project team for revision of 5300 & 5310 constituted Project proposal approved by FIPP Action items/Key next items To keep track of Progress

## Slide 6: Objective - 2
Enable wide exchange of knowledge and experience among INTOSAI members

## Slide 7: WGITA Webpage - INTOSAI Community Portal
Progress indicator | Action items and other comments
New Working group website in KSC-IDI INTOSAI Community Portal | Progress to date Functioning Working Group Website in INTOSAI Community Portal Action items/Key next items Identification of members to manage Website Collection of material for WGITA Knowledge Centre Contribution for Audit Report Database Identification of members for hosting Webinars etc.

## Slide 8: Generation and dissemination knowledge and experiences
Progress indicator | Action items and other comments
At least one Performance Audit Seminar and one International Audit Seminar on IT related topics before next INCOSAI | Progress to date International seminar on Audit Management System hosted by SAI Korea in 2017 Seminar on ‘’Embedding data assurance to drive audit efficiency and quality” hosted by ANAO, Australia in 2018 WGITA in coordination with GAO, USA holds triennial Performance Auditing Seminars (PAS) on topical subjects related to IT Audit. Action items/Key next items Next PAS seminar planned in 2019

## Slide 9: Generation and dissemination knowledge and experiences
Progress indicator | Action items and other comments
At least 5 country paper presentations on IT Audit related topics to be made integral part of every Annual WGITA meetings. | Progress to date Six country papers presented in WGITA Meeting at Seoul in 2017 Eight Country papers to be presented at 27th WGITA meeting Action items/Key next items Next Annual meeting scheduled in Fiji to continue current practice of country paper presentations Webinars for virtual presentations to be explored

## Slide 10: Objective - 3
Working with CBC, IDI, and other INTOSAI entities, facilitate continuous improvement of SAIs through knowledge sharing

## Slide 11: Stakeholder engagement - IDI
Progress indicator | Action items and other comments
In cooperation with IDI, next version of handbook would be updated before INCOSAI 2019 | Progress to date WGITA in collaboration with IDI developed an IT Audit Handbook which was approved by INCOSAI in 2013 Standing committee continuously updating WGITA-IDI Handbook and Plug-ins Action items/Key next items Handbook updation to be completed in line with QA process for non-IFPP products and as per IDI handbook on GPGs

## Slide 12: Stakeholder engagement - Regions
Progress indicator | Action items and other comments
Aim for greater cooperation with stakeholders | Progress to date AFROSAI-E and ISACA observers of WGITA involved in WGITA projects AFROSAI E part of two projects: General conditions for IT support for Audits and Documentation Requirements of an IT Audit including AMS. ISACA member of ISSAI 5310 revision project on IT Security including Cyber Security Participated in EUROSAI WGITA Meeting and presented on IT Audit Handbook Action items/Key next items Continue to engage with AFROSAI-E,ISACA and other regions

## Slide 13: Thank You