## Plan1
Initial | Final | Description
Current and future activities
2015-05-13 |  | Submission of the guide's current draft [Chapter I - IT Governance; Chapter II - Governance Evaluation Techniques for IT (GET.IT); Chapter III - Case Studies] group's revision.
Past activities
2015-04-10 | 2015-05-13 | Discussions about hosting a meeting of the group (SAI Brazil) during 2015, 2nd semester
2015-04-10 | 2015-05-13 | Overall revision and harmonization of the text by SAI Brazil.
2015-04-10 | 2015-05-11 | Reorganization of the "case studies" into a new chapter by SAI Kuwait.
2015-04-10 | 2015-05-05 | Development of the guide's introduction by SAI Lithuania.
2014-11-15 | 2014-12-15 | Chapter II's consolidation, review and approval.
2014-09-17 | 2014-11-15 | Development of Chapter II's sections by SAIs USA, South Africa, Brazil, Lithuania.
| 2014-11-11 | Submission of an additional case study by SAI South Africa.
2014-09-17 | 2014-10-01 | Team allocation for the production of Chapter II's four methodologies (Individual Organizations: USA; State-level: South Africa; Survey-based: Brazil; Self-assessment: Lithuania).
2014-09-17 | 2014-10-01 | Review of Chapter II's proposed structure.
2014-09-17 | 2014-10-01 | Review of the proposed Chapter I by SAI Lithuania.
| 2014-09-17 | Submission of project report for the WGITA Chair.
| 2014-09-17 | Submission of Chapter II's proposed structure and Chapter I draft for group review and approval.
| 2014-09-17 | Submission of three case studies (Brazil, Kuwait and Lithuania) for group review and approval.
2014-07-16 | 2014-09-15 | Development of Chapter I by SAI Brazil and case studies by SAIs Brazil, Kuwait and Lithuania.
2014-07-15 | 2014-08-15 | Discussion and review of the proposed structures for Chapter I and the "case studies" chapter.
| 2014-07-16 | Submission of the proposed structure for the guide's Chapter I (concepts and definitions) and for the chapter about group member SAIs' experience on IT governance induction and evaluation (case studies). Products: "proposed structure for the first chapter of the Governance Evaluation Techniques for IT (GET.IT) guide" and "proposed structure for the case study".
2014-02-10 | 2014-02-12 | 23rd WGITA Meeting (Kuwait): Marcelo Eira, then secretary of SAI Brazil's department of IT audit, described Brazil's IT Governance Index (iGovTI), its supporting questionnaire and survey methodology and presented the Governance Evaluation Techniques for IT (GET.IT) project to elaborate a guide containing: concepts and definitions of IT governance in the public sector; model for evaluation of IT governance for Supreme Audit Institutions; model for evaluation of the IT governance capacity for public organizations; support for future proposal of an IT governance evaluation model.
| 2013-11-26 | E-mail sent to team members requiring representative confirmation. Teams proposed. Acknowledgement received from SAIs USA and Kiribati.
| 2013-09-02 | Team members invited to comment project’s PID and synopsis and to share their experiences on IT governance evaluation. Comments received from SAI Lithuania and an information requirement from SAI South Africa.
2013-07-29 | 08/08/2013 | Side discussions during IDI/WGITA IT Audit Handbook working sessions in Shimla, India (SAIs India, USA, Brazil and Poland).
| 2013-07-08 | PID approval by the WGITA Chair.
| 2013-06-14 | Submission of PID for the WGITA Chair.
2013-05-01 | 2013-06-13 | Internal meetings (SAI Brazil) in order to produce PID proposal.
2013-04-25 | 2013-04-26 | Discussions and project proposal during 22nd Intosai's WGITA meeting (Lithuania).