## Slide 1: Development of ISSAI 5300 on IT AUDIT
Progress Report
A presentation by SAI India to WGITA

## Slide 2: Introduction - background
Series 5300-5399 of ISSAIs allocated to Guidelines on Information Technology Audit under the ISSAI framework
The Project - Development of ISSAI 5300: Guidelines on Information Technology Audits – was included in WGITA’s work plan 2014-16 in Vilnius, Lithuania (April 2013)
The WGITA meeting in Kuwait (April, 2014) approved the Project initiation Document which spelt out the details of the project, probable timelines, milestones and expected deliverables.
The KSC (Cairo, Egypt) approved the associated Project Proposal in October 2014.
Project Team
  Team Leader: SAI India
  Members – SAIs of Brazil, Indonesia, Japan, Norway, Poland, the US

## Slide 3: Progress since last WGITA in Kuwait, 2014
Approval of Project Proposal of ISSAI 5300 (October 2014)
  The Project Proposal approved by the KSC Steering Committee in Cairo (Egypt) in October 2014.
  The Project Proposal spells out the details of the project, the methodology proposed to be employed, probable timelines, milestones and expected deliverables.
IT Audit Survey (December 2014)
One of the key features of the ISSAI 5300 development process is to ensure that the proposed ISSAI takes into consideration:
  the existing levels of maturity of Information Systems in the government sector in different countries and
  the maturity level of IT Audits in their respective SAIs.

## Slide 4: Progress since last WGITA in Kuwait, 2014
To determine the above, the Project Team is in the process of conducting an INTOSAI wide IT Audit Survey
The Survey used a detailed Questionnaire aimed at generating a comprehensive database covering IT Audit practices, standards and manuals in use, etc. in order to determine the IT Audit related maturity and profile of SAIs world-wide. The Project Team intends to use the database for deriving required inputs for framing the ISSAI.
The maturity and usage profile generated from the Survey is proposed to be employed in determining the granularity the proposed ISSAI would aim for in order to have as wide an acceptability as possible amongst the INTOSAI community

## Slide 5: Progress since last WGITA in Kuwait, 2014
The IT Audit Questionnaire developed and circulated by the Project Team (December 2014) broadly covers following areas:
  IT Governance Setup in the country
  Recognition of IT Audit at a conceptual level in member SAI
  Mandate
  Maturity of IT Systems in the country
  The IT Audit Process
  Capability of the SAI in conducting IT Audits
Till date, 52 responses have been received from different INTOSAI members. The responses are being collated.

## Slide 6: Progress since last WGITA in Kuwait, 2014
Drafting of ISSAI 5300 (June 2015)
  The Project Team has prepared a draft skeletal draft of ISSAI 5300. (MAY 2015)
  The Skeletal Draft is at present being deliberated upon by the Project Team.
  A copy of this skeletal draft was also circulated amongst all WGITA members. (JUNE 2015)

## Slide 7: Proposals to WGITA - Proposed Amendments to the Project Schedule
The Project Schedule approved by the KSC needs to be revised.
The approved Project Schedule underestimates the multiple levels of approvals and endorsements required, as well as the complexity involved in arriving at a universally acceptable draft.
The Project Team therefore proposes a change in the Schedule.

## Slide 8: Proposed Amendments to the Project Schedule
The Project Team would attempt to finalise the draft ISSAI and then seek approval of the exposure draft by the WGITA and the KSC through email exchanges.
The exposure draft to be then exposed at the ISSAI website and comments of all INTOSAI members invited.
Simultaneously the exposure draft would also be run through the PSC.
The Project Team would then endeavour to have the final draft of ISSAI 5300 approved in next year's face to face meetings of the WGITA and the KSC.

## Slide 9: Proposal before the WGITA
WGITA members are requested to
  Take note of the Progress Report
  Approve the proposed revisions in the Project Schedule

## Slide 10: Thanks…