## Slide 1: Project Progress Report – “Roadmap for development of future GUIDs in the 5300 series”
Presentation by
SAI Pakistan

## Slide 2: Sequence of Presentation
Project Background
Project Team
Roadmap Document -- Objectives
Project Progress
Overview of Initial Draft – Roadmap Document
Future Activities
Proposals before WGITA

## Slide 3: 1. Project Background
The 25th WGITA Meeting was held at Brasilia from 26-27th of April 2016 at Brasilia, Brazil.
The WGITA Work plan 2017-19 comprising of 05 projects was approved.
Project #2 of this plan was :
  “Development of Roadmap for future ISSAIs in the 5300 Series”

## Slide 4: 2. Project team
Team Lead: SAI Pakistan
Team members:
  SAI Brazil
  SAI China
  SAI India
  SAI Japan
  SAI Korea
  SAI Poland
  SAI USA

## Slide 5: 3. Roadmap Document -- Objectives
To act as reference document for development of future GUIDs in the domain of IT Auditing.
It envisages development of future GUIDs in a logical manner.
It identifies significant subjects for development of future GUIDs.
The target group for the roadmap document are KSC and PSC of INTOSAI.

## Slide 6: 4. Project Progress
Activity | Time frame -- Dates
Draft Project Initiation Document (PID) was prepared | August 2016
Final PID after Input from team members submitted to WGITA Chair | October 2016
PID Approved | 23rd Oct. 2016
Draft Project Plan prepared | December 2016
Final Project Plan after input from team members prepared & submitted to WGITA Chair | March 2017
Project Plan Approved | May 2017

## Slide 7: 4.1 Change in Name of Project
In the XXII INCOSAI held at Abu Dhabi in December 2016, the INTOSAI Framework of Professional Pronouncements (IFPP) was approved and Strategic development plan (2017-19) for IFPP was initiated.
Accordingly the 5300 Series (that dealt with the subject of IT auditing) was shifted from ISSAIs to GUIDs or Guidance.
The title of project was hence modified as “Roadmap for development of future GUIDs in the 5300 Series”, through WGITA Chair.

## Slide 8: 4.2 Project Progress after last WGITA meeting
Activity | Time frame – Dates
Data acquisition and accumulation stages: Existing work done by WGITA was reviewed Current trends in IT landscape analyzed | June to Dec 2017
Relevant Inputs received from SAI China, SAI India, SAI Japan, SAI Korea and SAI USA | 
Based on all inputs received Initial Draft Roadmap prepared and circulated amongst team members | February, 2018
Feedback received from SAI USA and SAI India | March, 2018

## Slide 9: 5. Overview of Initial Draft -- Roadmap Document
The Roadmap document outlines its objectives and intended purpose.
It highlights the need for development of a roadmap.
It highlights how the globalized IT environment is effecting Auditing techniques and practices.
The “structure” for development of the roadmap is defined (fig on next slide)
It is developed as a “live document” to be reviewed periodically.

## Slide 10: Structure of the Roadmap
1. Analyzing the IT Landscape
Highlighting Specific/New IT Areas/Interventions/Solutions
Proposing Suitable GUID to cover audit requirement for a specific IT Area/Intervention/Solution

## Slide 11: 5. …continued
First the “Broad Contours of todays IT landscape” have been defined.
Co-relation between different IT areas highlighted.
Then a “linkage” is developed between the IT landscape and IT Audit requirements.

## Slide 12: Logical Linkage Between an IT Area and Audit Requirements
Specific IT Tools/Solutions
An IT Area
Audit Requirements
Analysis & Usage of the IT Area's manifestations

## Slide 13: 5 … continued
Lastly, subjects proposed for the development of future GUIDs’ in IT Auditing.
16 subjects have been proposed for future GUIDs in the present roadmap version.

## Slide 14: 5.1 Proposed subjects for future GUIDs

## Slide 15: 5.1 Proposed Subjects/Topics
Guidelines on IT Governance Audit
Guidance on IT Evidence collection & analysis
Guidance on formation of IT Materiality
Guidance on Audit of IT Development & Acquisition
Guidance on review of outsourcing IT services

## Slide 16: 5.1 ….continued
Guidance on Network Essentials review
Guidelines on Auditing Advance Networks & Cyber Security
Guidance on Cloud Computing Audit
Guidance on Audit of ERP systems
Guidelines on Audit of Database Management Systems (DBMS) including analytics

## Slide 17: 5.1 …continued
Guidelines on Big Data Audit
Guidelines on Audit of Information Systems Performance
Guidelines on Audit of Information Systems Sustainability
Guidance on Audit of Bank transactions
Guidance on Audit of E-governance
Guidelines on real-time auditing techniques

## Slide 18: 6.Future Activities:
The Initial Draft to be circulated amongst WGITA members for input and comments.
Final Draft to be submitted to WGITA Chair for approval by December 2018

## Slide 19: 7. Proposals before WGITA
To Take note of the project progress done so far.
To circulate the initial draft amongst all WGITA SAI members as well as observers for their feedback.
Finalized draft through WGITA Chair may be placed before relevant fora as a reference document.

## Slide 20: Thank You!