## Slide 1
WGVB MEXICO 2017
Jean-Raphaël Alventosa
Septembre 2017

## Slide 2: Presentation of the project of International Standard on jurisdictional activities

## Slide 3: PART A: PROJECT IDENTITY

## Slide 4: Project aim : To provide an internationally recognized standard to the jurisdictional activities of SAIs.

## Slide 5: This initiative could be considered as a part of the INTOSAI Strategic Plan 2017-2022, under Strategic Goal 1, Professional Standards, Strategic Objectives 1.2 “Ensure that the ISSAIs are sufficiently clear, relevant and appropriate to make them the preferred solution for INTOSAI’s members”.

## Slide 6: Project objectives: - Establish a common set of best practices in terms of jurisdictional activities - Support of the wider understanding of jurisdictional SAIs, including for SAI PMF assessment

## Slide 7: Project duration: 2 and half year

## Slide 8: Name of the lead WG: Working group on value and benefits of SAIs ( Forum of Jurisdictional SAIs)

## Slide 9: Other anticipated project team members SAI Chile, SAI Ecuador, SAI France, SAI Greece, SAI Morocco, SAI Peru, SAI Portugal, SAI Senegal, SAI Togo, SAI Turkey

## Slide 10: PART B: PROJECT MILESTONES 2017 - 2019

## Slide 11: Stage Due process milestones 1.Project proposal : 01.01.2017 to 01.09.2017 Depending on IFPP agenda IFPP = Intosai Framework of Professionnal Pronouncements

## Slide 12: 2. Exposure draft 02.09.2017 to 01.01 2019 1 year and 4 months

## Slide 13: 3. Exposure period and endorsement version 02.01.2019 to 01.08.2019 7 months

## Slide 14: 4. Final pronouncement, including translation 01.08.2019 INCOSAI XXIII –moscow - Nov 2019

## Slide 15: PART C: INITIAL ASSESSMENT AND PROJECT PROPOSAL

## Slide 16: C. 1 Explanation of the need and purpose for the project

## Slide 17: Around the world, 26% of the SAI undertake control activities of public finances considered as “jurisdictional” and built on the “Court of Account” model Today, the specific principles and practices of the jurisdictional control of SAIs are not included in the INTOSAI’s Professional Pronouncements Framework.

## Slide 18: The members of the Forum of SAI with Jurisdictional functions (FSAIJ) agreed unanimously of the necessity to create a working group, whose mission would be to help to integrate jurisdictional activities standardization within the INTOSAI Framework of Professional Pronouncements. The Association of French speaking SAIs (AISCCUF), associate member of INTOSAI, supports this initiative.

## Slide 19: C.2 Description of the categories of auditing or other engagements that will be covered by the new pronouncement(s)

## Slide 20: The purpose of the jurisdictional control activity performed by some SAIs is to judge the accounts submitted by the public accountants and, in some cases, the authorizing officers (managers) in their management activities.

## Slide 21: This jurisdictional control is not a substitute for compliance and performance audits but it supplements them. It is indeed the mission of the SAI with jurisdictional function to sanction non-compliance with public finance legislation.

## Slide 22: C.3 Description of different types of SAIs / audit engagements that must be accommodated in the new pronouncement

## Slide 23: The main specificity of SAIs with jurisdictional function is that they are entrusted with enforcing legislation and regulation. they create, over the years and the judgments that they give, a jurisprudence, which applies itself to the litigants.

## Slide 24: C.4 Explanation of how consistency other existing ISSAIs will be ensured

## Slide 25: The standard on compliance audit – ISSAI 4000- evidences loopholes with regard to the full range of jurisdictional activities. The drafting of the jurisdictional standard should complement the provision specific to jurisdictional SAI within the ISSAI 4000.

## Slide 26: C.5 Explanation of the organisation of the project

## Slide 27: Initially, the Forum of jurisdictional SAIs was created under the auspices of the Working group V and B of SAIs. now, this Forum gathers 33 SAIs with jurisdictional functions. Within this group, 10 SAIs volunteered to work on this project. However, only 3 of them are members of WGVBs. With the agreement of the Goal 3 Chair and the WG chair, the remaining SAIs could be included in WGVBS and form a sub-group to work in this topic . SAI Chile, SAI Ecuador, SAI France, SAI Greece, SAI Morocco, SAI Peru, SAI Portugal, SAI Senegal , SAI Togo, SAI Turkey

## Slide 28: C.6 Explanation of the quality processes that will be applied in the drafting process

## Slide 29: quality control will rest upon a constant dialogue with the IfPP, the members of the working group and, eventually, review by all the Jurisdictional SAIs of the Forum of jurisdictional SAIs.

## Slide 30: calendar: - Dec 2016 : Abu Dhabi : ratification of the Paris declaration of the forum of jurisdictional SAIs - January 2017 : redaction of the project proposal - July 2017 : submission to the KSC Chair, and adoption by the Chair - July Ottawa : submission to the IFPP : agreement - sept / oct 2017 : procedures with Chairs of VB, KSC, and PSC - nov 2017 : first meeting of the WG on Jur activities - 2018 : plenary meeting of the forum of Jur Sais

## Slide 31: Thank you for your attention !